## Registration Tracker
AI Platform Registration & Status Tracker
Wike-Young Kennedy Hachimeganum ¦ Port Harcourt, Nigeria
Track every platform: registration, verification, qualification, and first earnings.
Platform | Website | Priority | Registered? | Date Registered | Profile Complete? | ID Verified? | PayPal Connected? | Qualification Test | Test Score/Result | First Task Date | First Earning ($) | Status | Notes
CrowdGen (Appen) | crowdgen.com | TIER 1 | [9 empty] | Not Started | Register first. Highlight Ikwerre + English skills.
TELUS Digital | telusinternational.ai | TIER 1 | [9 empty] | Not Started | Prepare for search evaluation assessment.
Prolific | prolific.com | TIER 1 | [9 empty] | Not Started | Complete demographic profile fully for more studies.
Alignerr | alignerr.com | TIER 2 | [9 empty] | Not Started | Complete AI interview with Zara. Test Nigeria access.
Welocalize | welodata.ai | TIER 2 | [9 empty] | Not Started | Emphasize Ikwerre language for localization projects.
Mercor | work.mercor.com | TIER 2 | [9 empty] | Not Started | Apply and test. If blocked, move on immediately.
Outlier | outlier.ai | TIER 3 | [9 empty] | Not Started | May be geo-blocked. Try once, accept result.
Dropdown Options:
Registered? = Yes / No / Blocked
Status = Not Started / Registered / Testing / Active / Earning / Blocked / Paused

## Daily Activity Log
Daily Activity & Earnings Log
Log every work session. Track hours, tasks, quality scores, and earnings by platform.
Date | Day # | Platform | Hours Worked | Tasks Completed | Task Type | Quality Score | Earnings ($) | Cumulative ($) | Payment Received? | Notes / Issues
2026-07-30 | 1
2026-07-31 | 2
2026-08-01 | 3
2026-08-02 | 4
2026-08-03 | 5
2026-08-04 | 6
2026-08-05 | 7
2026-08-06 | 8
2026-08-07 | 9
2026-08-08 | 10
2026-08-09 | 11
2026-08-10 | 12
2026-08-11 | 13
2026-08-12 | 14
2026-08-13 | 15
2026-08-14 | 16
2026-08-15 | 17
2026-08-16 | 18
2026-08-17 | 19
2026-08-18 | 20
2026-08-19 | 21
2026-08-20 | 22
2026-08-21 | 23
2026-08-22 | 24
2026-08-23 | 25
2026-08-24 | 26
2026-08-25 | 27
2026-08-26 | 28
2026-08-27 | 29
2026-08-28 | 30
2026-08-29 | 31
2026-08-30 | 32
2026-08-31 | 33
2026-09-01 | 34
2026-09-02 | 35
2026-09-03 | 36
2026-09-04 | 37
2026-09-05 | 38
2026-09-06 | 39
2026-09-07 | 40
2026-09-08 | 41
2026-09-09 | 42
2026-09-10 | 43
2026-09-11 | 44
2026-09-12 | 45
2026-09-13 | 46
2026-09-14 | 47
2026-09-15 | 48
2026-09-16 | 49
2026-09-17 | 50
2026-09-18 | 51
2026-09-19 | 52
2026-09-20 | 53
2026-09-21 | 54
2026-09-22 | 55
2026-09-23 | 56
2026-09-24 | 57
2026-09-25 | 58
2026-09-26 | 59
2026-09-27 | 60
2026-09-28 | 61
2026-09-29 | 62
2026-09-30 | 63
2026-10-01 | 64
2026-10-02 | 65
2026-10-03 | 66
2026-10-04 | 67
2026-10-05 | 68
2026-10-06 | 69
2026-10-07 | 70
2026-10-08 | 71
2026-10-09 | 72
2026-10-10 | 73
2026-10-11 | 74
2026-10-12 | 75
2026-10-13 | 76
2026-10-14 | 77
2026-10-15 | 78
2026-10-16 | 79
2026-10-17 | 80
2026-10-18 | 81
2026-10-19 | 82
2026-10-20 | 83
2026-10-21 | 84
2026-10-22 | 85
2026-10-23 | 86
2026-10-24 | 87
2026-10-25 | 88
2026-10-26 | 89
2026-10-27 | 90
TOTALS

## Weekly Milestones
90-Day Weekly Milestones
Check off each milestone as you complete it. Be honest.
Week | Phase | Milestone | Target Date | Completed? | Actual Date | Notes
1 | Phase 1: Foundation | Create professional Gmail account (wikeyoung41@gmail.com) | 2026-08-05
1 | Phase 1: Foundation | Set up PayPal Nigeria account and complete verification | 2026-08-05
1 | Phase 1: Foundation | Create Payoneer account as backup payment method | 2026-08-05
1 | Phase 1: Foundation | Set up dedicated workspace with reliable internet | 2026-08-05
1 | Phase 1: Foundation | Register on CrowdGen (crowdgen.com) - complete full profile | 2026-08-05 |  |  | Highlight Ikwerre + English
1 | Phase 1: Foundation | Register on TELUS Digital (telusinternational.ai) | 2026-08-05
1 | Phase 1: Foundation | Register on Prolific (prolific.com) - complete demographic profile | 2026-08-05 |  |  | Fill in ALL details
2 | Phase 1: Foundation | Register on Alignerr (alignerr.com) - complete AI interview | 2026-08-12 |  |  | Test Nigeria availability
2 | Phase 1: Foundation | Register on Welocalize/Welo Data (welodata.ai) | 2026-08-12 |  |  | Emphasize Ikwerre language
2 | Phase 1: Foundation | Register on Mercor (work.mercor.com) - test access | 2026-08-12 |  |  | If blocked, move on
2 | Phase 1: Foundation | Attempt Outlier registration (outlier.ai) | 2026-08-12 |  |  | May be geo-blocked
2 | Phase 1: Foundation | Take typing speed test (target: 30+ WPM) | 2026-08-12 |  |  | Use 10fastfingers.com
3 | Phase 1: Foundation | Begin CrowdGen qualification tests | 2026-08-19 |  |  | Study guidelines first!
3 | Phase 1: Foundation | Complete TELUS Digital assessments | 2026-08-19 |  |  | Search evaluation practice
3 | Phase 1: Foundation | Start accepting Prolific studies | 2026-08-19 |  |  | Build track record
3 | Phase 1: Foundation | Take Welocalize language proficiency tests | 2026-08-19 |  |  | English + Ikwerre
4 | Phase 1: Foundation | Complete all pending qualification tests | 2026-08-26
4 | Phase 1: Foundation | Earn first payment on ANY platform | 2026-08-26 |  |  | Track in Daily Log
4 | Phase 1: Foundation | Review and update all platform profiles | 2026-08-26
5 | Phase 2: Momentum | Achieve consistent 3-5 hour daily work schedule | 2026-09-02
5 | Phase 2: Momentum | Maintain quality score above 90% on all active platforms | 2026-09-02
5 | Phase 2: Momentum | Reach $20-$80 total earnings milestone | 2026-09-02
6 | Phase 2: Momentum | Apply for specialized projects on active platforms | 2026-09-09 |  |  | Translation, localization
6 | Phase 2: Momentum | Create LinkedIn profile (linkedin.com) | 2026-09-09 |  |  | Title: AI Data Annotator
6 | Phase 2: Momentum | Start basic prompt engineering learning (free course) | 2026-09-09 |  |  | LearnPrompting.org or YouTube
7 | Phase 2: Momentum | Improve typing speed to 35+ WPM | 2026-09-16 |  |  | Daily practice
7 | Phase 2: Momentum | Reach $100-$150 total earnings | 2026-09-16
7 | Phase 2: Momentum | Network with Nigerian contributors on Reddit | 2026-09-16 |  |  | r/WFHJobs, r/WorkOnline
8 | Phase 2: Momentum | Drop platforms with no income (OneForma, Handshake) | 2026-09-23 |  |  | Stop wasting time
8 | Phase 2: Momentum | Reach $200-$300 total earnings | 2026-09-23
9 | Phase 3: Optimization | Focus on best-performing 2-3 platforms only | 2026-09-30
9 | Phase 3: Optimization | Apply for domain-specific projects (coding, translation) | 2026-09-30 |  |  | If skills allow
10 | Phase 3: Optimization | Begin learning basic Python (freeCodeCamp) | 2026-10-07 |  |  | Opens coding tasks
10 | Phase 3: Optimization | Update CV with actual AI training experience | 2026-10-07
11 | Phase 3: Optimization | Typing speed 40+ WPM | 2026-10-14
11 | Phase 3: Optimization | Reach $300-$450 total earnings | 2026-10-14
12 | Phase 3: Optimization | Explore direct freelance AI training opportunities | 2026-10-21 |  |  | Beyond platforms
12 | Phase 3: Optimization | Set minimum hourly rate based on actual data | 2026-10-21
13 | Phase 3: Optimization | 90-DAY REVIEW: $300-$600 total earnings target | 2026-10-28 |  |  | Typical: $400-$500

## Payment Tracker
Payment & Earnings Tracker
Track every payment received. Verify against platform dashboards.
Date | Platform | Amount ($) | Method | Reference/Transaction ID | Received? | Date Received | Notes
TOTAL

## Quick Reference
Quick Reference Card
Keep this open while working. Key info at a glance.
YOUR DETAILS
Name | Wike-Young Kennedy Hachimeganum
Email | wikeyoung41@gmail.com
Phone | +234 816 012 4516
Location | Port Harcourt, Rivers State, Nigeria
Languages | English (Fluent), Ikwerre (Native), Igbo (Partial)
PAYMENT ACCOUNTS
PayPal Email | wikeyoung41@gmail.com | Set up before first task
Payoneer | [Set up at payoneer.com] | Backup payment method
PLATFORM LOGIN URLs
CrowdGen | https://crowdgen.com
TELUS Digital | https://www.telusinternational.ai
Prolific | https://www.prolific.com/participants
Alignerr | https://app.alignerr.com/signin
Welocalize | https://welodata.ai/join-the-community
Mercor | https://work.mercor.com/login
Outlier | https://outlier.ai
DAILY TARGETS
Minimum Work Hours | 3-5 hours/day
Target Quality Score | 90%+
Target Typing Speed | 40 WPM by Day 90
Earnings Target (Day 30) | $20-$80 | Conservative
Earnings Target (Day 60) | $100-$300 | Conservative
Earnings Target (Day 90) | $300-$600 | Conservative / Typical
CRITICAL RULES
Rule 1 | NEVER use ChatGPT/AI to complete tasks | Instant permanent ban
Rule 2 | NEVER use VPN to bypass geo-restrictions | Instant permanent ban
Rule 3 | ALWAYS read task guidelines before starting | Prevents rejected work
Rule 4 | NEVER share your account | Instant permanent ban
Rule 5 | ALWAYS maintain quality score above 90% | Prevents project loss
Rule 6 | If a platform has no tasks for 2 weeks, move on | Do not waste time waiting
Rule 7 | Log every session in Daily Activity Log | Track progress
SKILLS TO LEARN
Priority 1 | Typing speed improvement (practice daily) | 10fastfingers.com
Priority 2 | Prompt engineering basics | LearnPrompting.org
Priority 3 | Basic Python (for coding tasks) | freeCodeCamp.org
Priority 4 | Advanced reading comprehension | Read technical articles daily